{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["立行立改台帐周报告6.16"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"立行立改台帐周报告6.16","index":0,"n_rows":99,"n_cols":9,"rows_kept":99,"merged":[[0,0,0,7],[92,1,93,1]],"flags":["formulas_cached_only"]}
["党的群众路线教育实践活动立行立改台帐整改落实进度及完成情况周通报（6月16日）"]
["序号","问题与建议","牵头责任部门","整改措施","整改时限","责任人","责任校领导","反馈形式","整改落实进度及完成情况周报告"]
[1,"刚进学校交了书本费，但大学生体育和计算机教材对我们没有很大作用，我们专业课程比较多，能不能把我们不用的书换成我们专业的书？","教务处","待大一新生入学后，再次征求已交书费学生的意见，确认购买的各种书籍","9-10月","刘国良\n赵艳萍","房海","具体情况找教务科教材管理人员反映"]
[2,"教室教堂设备更换不及时，B206激光笔；北院，要求老师站着讲课，多媒体太矮，需加高；教务部门服务意识差，对于多媒体等教学设施管理维修不利，教学环境差，影响老师的上课质量与进度，但却从不对此后果负责；学校的设备，多媒体，窗帘，灯管，水管等都坏了，希望能及时修理；多媒体教室，电脑开机太慢，投影灯泡老化，显示屏很脏；各教室设备老化问题。投影仪噪声太大A111，保证教堂设备正常使用。后院多媒体网络何时安装到位，没网络一些课开不了；多媒体教室设备陈旧，时常死机；投影仪电脑老化，效果不好；电子教室间互相影响；教学设备","教务处","1.教务处专门在每个教室发放了多媒体事故报告单，专门下发了多媒体教学设备的使用操作说明，根据实际及时维修；2.责成教室管理科在桌面做了事故报告的友情提示；3.所有多媒体教室均有固定话筒，在200人以上的大教室配备了移动话筒，90人以上的教室，若教师确实需要，可申请；4.现已在多媒体电脑的桌面进行了警告和提醒，但秦皇岛校区北院有些需设备更新，学校已批经费，经采购，暑假后到位。开发区校区实施中控管理","即时","刘国良\n周铁军","房海",null,"104教室的多媒体设备教务处已进行更新"]
[3,"自习室紧张问题","教务处","1.公布教室占用信息2.开发区和昌黎校区，已安排了相对固定的数量充足的考研教室，秦皇岛校区可适当增加\n3.秦皇岛校区学生晚上占用教室活动，尽量安排到北院\n4.清理私自占用教室","秦皇岛校区已实现，其他校区5月底以前","刘国良\n阴立群","房海","网络公布","三个校区均已安装电子大屏幕"]
[4,"网络选课期间有时选不上课的问题","教务处","1.建议由网络中心提高网速；2.延长选课时间；3.提供补选机会4.通过教学信息发布屏发布","选课期间","刘国良\n阴立群","房海","网络公布"]
[5,"课表不人性化，有时前几周课较少，有时又集中上课，前松后紧。有的前两节在后院，后两节在前院","教务处","1.充分考虑课程的均衡；\n2.除特殊情况，不安排前后院的衔接上课，若有问题及时调整 ","本学期排课\n时实现","刘国良\n阴立群","房海","网络公布"]
[6,"教学档案电子化管理问题 ","教务处","推行","从现在开始","刘国良\n阴立群","房海","网络公布"]
[7,"学生选修课问题","教务处","根据教师、学生情况安排重复班","本学期选课开始","刘国良\n阴立群","房海","网络公布"]
[8,"机房设备陈旧问题","教务处","已立项等待采购后进行更新","采购后","王树元\n尹秀玲","房海","网络公布"]
[9,"对耗材消耗较多的各级各类技能大赛支持问题","教务处","向学校建议，增加学科竞赛经费，解决院（系）经费不足（可调剂）","据参赛项目即时调整","王树元\n尹秀玲","房海","网络公布"]
[10,"提高实验室仪器设备的利用率问题","教务处","做好管理制度的督促落实","已于2013年底公布文件","王树元\n尹秀玲","房海","网络公布"]
[11,"实习基地不好找，给予实习费用要求正式发票，既然增加了二级学院权利，报账能不能方便一些","教务处","已出台了新的报销制度（参看教务公告），报销环节已简化。财务问题我处无权解释","已改","王树元\n尹秀玲","房海","网络公布"]
[12,"实习基地费用报销问题","财务处","用白条报销，不符合财务管理规定","解释","于红军","王同坤","网络公布","已落实"]
[13,"学生管理制度宣传效果不够问题","学生处","加强制度宣传普及工作，对制度落实工作进行督导检查","正在做","徐树君","张福喜","会议网络","已落实"]
[14,"社团收费问题","团委","已整改","5月份","于海印","张福喜","会议网络","已落实"]
[15,"校级学生组织管理问题","团委","对制度落实进行督办","正在做","于海印","张福喜","会议网络","正在落实"]
[16,"三金评定问题","学生处","加强制度学习、对制度落实进行督办","认定贫困生时段","宋文华","张福喜","会议网络","在认定贫困生时段落实"]
[17,"上课期间宿舍应该限电问题","学生处","调研论证可行性","5-6月份","徐树君","张福喜","网络公布","已完成（结论：不可行）"]
[18,"加强校内教师之间的学术交流，内部评价问题","科研处","项目申报及成果实行公示制度","5月","闫立英","杨越冬","网络公布","已落实"]
[19,"实用新型专利奖励问题","科研处","校科字〔2013〕7号文件中已有相关奖励办法","已执行","闫立英","杨越冬","网络公布","已落实"]
[20,"关于学术讲座问题","科研处","按照2014学术讲座计划组织实施。校园网学术活动专栏公布","常年","闫立英","杨越冬","网络公布","已落实"]
[21,"开拓科研信息渠道问题","科研处","学校一直尽力拓展各类项目申报渠道，为教师提供服务","常年","闫立英","杨越冬","网络公布","已落实"]
[22,"实习基地费能否用不规范票据报销问题","财务处","以不规范票据报销不符合财务管理规定","立改","于红军","王同坤","网络公布","已落实"]
[23,"秦皇岛校区一食堂看着不正规问题","校园规划与国资处","按照学校计划，建设新食堂和浴室等学生生活设施","年内开工","杨洪青","郭国维","网络公布","项目核准证已办回，正在办理《建设工程规划许可证》和《建设工程施工许可证》"]
[24,"就餐环境改善问题","后勤集团","已解决","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[25,"开发区校区餐厅教工窗口问题","后勤集团","已开设","已落实","苏小滨","郭国维","网络公布","已落实"]
[26,"职工自助餐模式推广问题","后勤集团","已解决","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[27,"餐饮中心环境、卫生问题","后勤集团","已传达给餐饮中心督促改进中","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[28,"消毒柜消毒问题","后勤集团","昌黎校区：已经购置消毒柜，近期到货\n秦皇岛校区：筷子已经用蒸汽、以及热风式消毒柜消完毒 \n开发区校区：已配备两台筷子热风消毒机，彻底解决筷子消毒问题 ","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[29,"食堂伙食多样化，开放时间问题","后勤集团","增加主副食品种，视情况予以延长售饭时间\n","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[30,"食堂水资源浪费问题","后勤集团","五月初进行餐饮水电量普查和维修，更换水龙头，加强员工教育，监督台配合","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[31,"食堂就餐不排队问题","后勤集团","排队标志已做，设立监督台后可起到引导作用","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[32,"学生食堂需要学校领导的关心问题","后勤集团","加强餐厅卫生管理、主副食品种已经找保洁公司，五一期间进行食堂公共卫生清理（门窗），已要求中心任、管理人员在售饭期间进行各食堂巡视，主管副总每周不少于五次（含周六周日），分开早中晚时段；五月份召开伙专会，设立监督台","5.20","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[33,"食堂环境、食品卫生问题","后勤集团","规范员工着装标准，建立处罚机制，同学们监督 ，建立每日一小扫、每周一大扫的卫生制度，努力提高饭菜口感及质量，为同学们提供更好的就餐环境.","5月底","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[34,"食堂晚餐适应南方学生问题","后勤集团","已通知各食堂增加；引进南方小吃","5.30","苏小滨王宏伟","郭国维","网络公布","已落实"]
[35,"学生公寓安全防范问题","后勤集团","加强值班管理","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[36,"学生公寓不安全，一楼经常丢失衣服严重问题（二号女生楼）","后勤集团","加强值班管理与安全巡视，1-5楼安装防护网","6.20","王敏刚","郭国维","网络公布","已落实"]
[37,"宿舍安全问题（7号楼丢电脑）","后勤集团","增加安全员重点巡查","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[38,"男员工随便进宿舍（10号楼、北2宿舍楼一层）","后勤集团","加强值班管理","已落实","王敏刚","郭国维","网络公布","已落实"]
[39,"北3宿舍橱柜太高问题（1－5同）","后勤集团","给学生配备小梯子","已落实","王敏刚","郭国维","网络公布","已落实"]
[40,"宿舍厕所、水房卫生差问题","后勤集团","增加人员，改进处理","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[41,"财经班级人多，教室小桌椅不够问题","后勤集团","根据教室容量合理增加","已落实","王敏刚","郭国维","网络公布","已落实"]
[42,"学生教室桌椅乱搬，不够问题","后勤集团","清查后配齐 建立定期清查长效机制","4.25已完成清查配备","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[43,"学校路灯有些暗，安全性不高","后勤集团","加强检查，及时更换灯泡","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[44,"昌黎校区5号楼楼道的灯太暗、科研楼往东方向的路灯太暗问题 ","后勤集团","3号楼以东道路将庭院灯改为小型马路弯灯，提高路灯下照环境和亮度","已落实","王宏伟","郭国维","网络公布","已落实"]
[45,"教学楼照明问题","后勤集团","适当调整开灯时间 ","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[46,"宿舍楼道光线太暗问题","后勤集团","研究解决","5月底","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[47,"曙光公寓问题","后勤集团","（1）投币机坏时，请同学到值班室报修，值班员登记并通知厂家，保证24小时内维修；（2）投币后无法洗衣服时，请同学自行检查洗衣机进水管是否关闭；如无法自行解决，请同学到值班室登记宿舍号、姓名，待厂家取款时给予退款","即时","王宏伟","郭国维","网络公布","已落实"]
[48,"学校的设备，多媒体，窗帘，灯管，水管等维修补充问题","后勤集团","正在排查、维修，窗帘正在统计，多媒体需要协调网络中心，篮球板、篮球框已协调国资处","5.20","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[49,"桌椅好多都坏了","后勤集团","已安排全面检修，正在进行中","7月","王敏刚苏小滨王宏伟","郭国维","网络公布","截止6月8日已完成现运行桌椅的维修，今后加强日常检查与维护，每年寒暑假例行全面检修。"]
[50,"昌黎校区好多教室的地面、桌椅、内部环境维修和护理问题","后勤集团","安排全面检修","7月","王宏伟","郭国维","网络公布","已落实"]
[51,"部分宿舍床栏杆维修问题","后勤集团",null,"1.5.15初步完成维修;2.7-8月更换","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[52,"维护报修问题","后勤集团","加强日常报修管理，严格落实维修管理制度，提高维修及时率，并做好反馈\n已经启用维修报修短信平台，地址http://hqbx.hevttc.edu.cn或者后勤集团登陆页的网上报修，和公共网络均可登录，从而形成网络、电话、口头等多渠道报修和维修管理形式。面向师生员工发通知","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[53,"操场环境问题","后勤集团","秦皇岛校区：增加绿化人员，加强绿化，减少起尘原因；已启动塑胶操场建设项目\n昌黎校区：树木整体修整，局部裸土翻整、种植花草，局部硬化。操场局部硬化、护栏安装工程正在实施","5.31","王敏刚苏小滨","郭国维","网络公布","已落实"]
[54,"供水时间及温度问题","后勤集团","1.目前适当调整供水时间（水房开水温度：由于目前学生人数增加，1吨锅炉无法满足目前出水）；2.学校启动新食堂、浴室和水房建设项目","年内开工","王敏刚苏小滨王宏伟","郭国维","网络公布","年内开工(学校计划）"]
[55,"晚自习后水房增加一次供水问题","后勤集团","已延长打水时间","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[56,"水票问题","后勤集团","加强看管并及时安排解决(开发区校区已不再使用水票）","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[57,"开发区水卡问题","后勤集团","已联系鹏远公寓，已新安装一个正在试运行，如果学生用着方便将大批量安装，暑假期间安装完毕 ","7-8月","苏小滨","郭国维","网络公布","正在试运行，7-8月批量安装"]
[58,"设置电热水器问题","后勤集团","引自来水公司水计划已批准，正在联系自来水公司施工。考虑热水器电负荷较大，可逐步推行，先在一层配置热水器，教师、学生使用一卡通打开水，在秦皇岛、开发区可先开展","暑期","王敏刚苏小滨王宏伟","郭国维","网络公布","正在制定供水方案和楼宇负荷"]
[59,"教室清洁问题、教学楼宇垃圾筒设置问题","后勤集团","加强管理，严格要求","已落实","王敏刚","郭国维","网络公布","已落实"]
[60,"操场、花园多设置一些垃圾筒","后勤集团","购置垃圾箱计划已经批准，正在组织购买。正在落实","秦皇岛校区：7.31\n昌黎校区：5.15","王敏刚苏小滨","郭国维","网络公布","已落实"]
[61,"个别学生公寓的公共卫生环境太差问题","后勤集团","加强管理，严格要求","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[62,"宿舍地面破损问题","后勤集团","联合普查，较为严重地及时维修，严重或者存在普遍无法修葺的更新地面，报计划改造","暑期","王敏刚苏小滨王宏伟","郭国维","网络公布","待学生离校后统一进行"]
[63,"混合宿舍难管理问题","后勤集团","结合毕业进行调整","7.20","王敏刚苏小滨王宏伟","郭国维","网络公布","已完成初步沟通，待毕业生离校后初步进行整合，提出方案研讨。"]
[64,"开发区4号楼男生楼没有小便池问题 ","后勤集团","已与育星公司联系，要求暑假整改 ","7-8月","苏小滨","郭国维","网络公布","学生离校后整改"]
[65,"宿舍管理难度大，公共区域有死角，灯光太暗问题","后勤集团","实施垃圾袋装化，查摆环境卫生、宿舍管理薄弱环节，及时修复、安装灯具。购置垃圾桶、袋，加强环境卫生宣传和督导、树立员工岗位意识，5月底前进行一次集中检查，重点考察夜间照明情况，对卫生、照明的死角配齐设施和安装灯具","暑期","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[66,"有的宿舍人多东西放不下问题","后勤集团","研究后改进","暑期","王敏刚苏小滨王宏伟","郭国维","网络公布","本周已完成汇总数据"]
[67,"宿舍限电时间太早、夏天太热问题","后勤集团","计划在夏季到来前将越千年、曙光、芳园南、芳园北、同鑫、鑫园公寓架设防晒网，解决屋面防热，可降低屋面温度3-5摄氏度","6-7月","王敏刚苏小滨王宏伟","郭国维","网络公布","正在准备初步试行"]
[68,"宿舍用电15度/间，宿舍人多用电花消大，8号楼","后勤集团","按文件规定执行","5月底","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[69,"开发区2号楼水房插卡的机器有部分损坏，排水不方便","后勤集团","已联系鹏远公寓，已新安装一个正在试运行，如果学生用着方便将大批量安装，暑假期间安装完毕","7-8月","苏小滨","郭国维","网络公布","正在试运行，暑假期间安装完毕"]
[70,"洗澡，打卡付费，适当控制用水量","后勤集团","正在逐步进行改造，正在调研预算","暑期","王敏刚苏小滨王宏伟","郭国维","网络公布","正在预算"]
[71,"周末自习室锁门问题","后勤集团","前一段时间教室治理，现已无这种状况","已落实","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[72,"入学时购买被褥质量问题","后勤集团","后勤集团发放的备品为河北省统一招标产品，均有质量检测报告，新生入学时为自愿购买，从未强制购买","9.10","王敏刚苏小滨王宏伟","郭国维","网络公布","已落实"]
[73,"开发区公寓2号楼西边安装安全护栏问题","后勤集团","此处为消防通道，不能安装护栏，原有护栏2009年已被消防部门通知拆除","因消防规定无法安装","苏小滨","郭国维","网络公布","因违反消防规定无法安装"]
[74,"设备采购有关问题","建设采购中心","采购管理办法已于5月份出台 中心将在5月期间召开各校区工作座谈会就相关问题进一步征求意见","5月下旬","杨静侠","李佩国","现场解释与网络宣传","昌黎校区已开座谈会"]
[75,"实验设备申购手续多、周期长问题","国资处建设采购中心","关于设备购置论证管理办法与采购管理办法分别于3月份和5月份相继出台，召开座谈会进一步征求意见","5月下旬","杨静侠","李佩国","现场解释与网络宣传","昌黎校区已开座谈会"]
[76,"贴吧不良信息处理问题","网络中心","建立舆情监测机制购进舆情秘书，时刻留意各主要论坛及贴吧的情况，及时发现不良和不实信息","6月份","张海涛薛文辉","房海","网络公布","舆情秘书正在试用阶段，通过学校论证，确认购买正式版本替换试用版本"]
[77,"秦皇岛校区北院多媒体网络问题","网络中心","综合布线，把多媒体教室接入校园网","4月底","张海涛孙志文","房海","网络公布","已落实"]
[78,"开发区网速慢问题","网络中心","增大网络出口带宽，增加网络管理系统，合理利用网络，增加网络加速设备","7-8月","张海涛孙志文","房海","网络公布","已完成线路规划，正进入设备申报环节,暑期进行线路改造,试用设备性能测试通过"]
[79,"外网登录校园网问题","网络中心","建设vpn通道，实现校内资源共享","已统一申请开通","张海涛孙志文","房海","网络公布","已落实"]
[80,"昌黎校区校园秩序管理问题","保卫处","昌黎校区东家属区增设蓝牙门禁系统","6月完成","吴子国   陈建新","张福喜","网络公布","已落实"]
[81,"宿舍楼灭火器不足问题","保卫处","1.按规定配足配齐我校所属的学生公寓楼灭火器；2.与后勤集团一起督促校外公寓楼经营公司配足配齐灭火器","7月完成","吴子国   陈建新","张福喜","网络公布","正在进行"]
[82,"外事公务接待有不节俭问题","国际合作与交流处","外事接待控制出席人员数量和接待规格，不购买过高的外事礼品，外事接待做到有礼有节","按年度公示","东方阳","王同坤","公示","已起草文件待校领导审核"]
[83,"昌黎校区图书馆有关化学、英语书籍借阅问题","图书馆","书库调整，新增一个开架书库","已开放","宋和平","高书国","网络公布","已落实"]
[84,"开发区七楼图书馆新书借阅问题","图书馆","文法学院自己购置的图书，图书馆负责分编 ","已借阅 ","宋和平","高书国","网络公布","已落实"]
[85,"图书馆周四下午开馆问题","图书馆","调整周四下午学习时间，开馆","5月份已实施 ","宋和平","高书国","网络公布","已落实"]
[86,"建外文数据库问题","图书馆","购置施普林格全文数据库","5月份完成","宋和平","高书国","网络公布","已落实"]
[87,"图书馆自习室问题","图书馆","增加阅览座位400个","8月前","宋和平","高书国","网络公布","启动招标阶段"]
[88,"领导校区值班问题","办公室","从6月起，每周公布领导值班和工作安排","6月初","蒋爱林赵彦军","李佩国","网络公布","已落实"]
[89,"毕业前证书、资料盖章问题","办公室","与教务处、就业处等部门做好协调与盖章工作","5月底","蒋爱林赵彦军","李佩国","网络公布","已落实"]
[90,"行政用房调整 ","办公室","制定办公用房使用实施方案，严格用房调整","4月份已拿出基本方案，并按活动办部署整改 ","蒋爱林赵彦军王荣加","李佩国","网络公布","正在推进"]
[91,"印发纸质文件意义不大问题","办公室","除党委常委会、校长办公会纪要、学校重大改革文件、存档外，不再印发纸质，做好网络信息发布工作","立改","蒋爱林王荣加","李佩国","网络公布","已落实"]
[92,null,"网络中心","建立校级协同办公系统平台，提高各部门的办公效率，使学校日常办公实现无纸化、自动化和网络化，改进和提升学校现代化管理水平，促进学校内部信息资源交流，解决信息孤岛的问题","6月份","张海涛崔勇","校园数字化建设领导小组","网络公布","办公系统平台已搭建完成，正在进行流程确认，办公流程确认完成，即进入系统试运行阶段"]
[93,"部分行政部门存在事难办、脸难看的问题 ","纪委办、监察处牵头，组织部、人事处、党办校办配合","1.设立举报电话和邮箱。2.对简单粗暴、吃拿卡要等行为进行纪律处理","常年","赵宗宝    ","孙雪莲","网络公布","1.已设立举报电话和邮箱；2.正在进行。"]
[94,"行政效能问题","纪委办        监察处","加强执纪监督检查","常年","赵宗宝    ","孙雪莲","网络公布","正在进行"]
[95,"校区间干部有相互宴请问题","纪委办   监察处   审计处","1.加强勤俭节约、廉洁自律教育2.对违反八项规定、“六个禁止”等违纪违规行为严肃查处 ","常年","赵宗宝          李  海","孙雪莲","网络公布","1.向领导干部发放了廉政教育材料；                          2.正在进行。"]
[96,"教授名师橱窗问题","宣传部","适时推出重点学科主要师资橱窗专版","9月底之前","赵建平","宋绍富","网络公布","正在进行"]
[97,"充分发挥电子显示屏宣传效果的问题","宣传部","1.在现有的校园LED屏显示内容中增加大学校园公益广告内容。2.结合校园传媒加强宣传","1.立改2.年底前","赵建平姜亚东","宋绍富郭国维","网络公布","正在进行"]